## Folha1
| Game | App | Server | Description | Possible Problems?
2020-11-13 | Camera Following the player & player center | UI concepts to Android Studio | *Undefined* | Nuno
2020-11-13 | PlayerMovement And Static UI | UI concepts to Android Studio | DataBase | Gabriel
2020-11-20 | Player Attack and Defense | Connection of main UI to their pages | *Undefined* | Nuno
2020-11-20 | Player Attack and Defense | Connection of main UI to their pages | DataBase Connectec to the server | Gabriel
2020-11-27 | Npc conversation with the player | Account & Log in | *Undefined* | Nuno
2020-11-27 | Archer enemy - Combat with Enemty Archer | *Undefined* | Log'in verification | Gabriel
2020-12-04 | Items & NPC Sentences | Item Creation in Kotlin | Solve of Problems if exist | Nuno
2020-12-04 | Level System and formulas | The draw and disposal of the item stats | Improvement of Database | Gabriel
2020-12-11 | *Undefined* | Map of the game Implementation in kotlin | Comunication with the Database | Nuno
2020-12-11 | Interface - Inventory & Interface - Item Store | *Undefined* | Comunication with the Database | Gabriel
2020-12-18 | Basic Item Balanciation | STATS of the player in the companion App | Solve of Problems if exist | Nuno
2020-12-18 | Enemy level system and formulas | STATS of the player in the companion App | Solve of Problems if exist | Gabriel
2020-12-25 | Playable Levels with Enemies | TRAINING SYSTEM in the companion app | Solve of Problems if exist | Nuno
2020-12-25 | Playable Levels with Enemies | TRAINING SYSTEM in the companion app | Solve of Problems if exist | Gabriel
2021-01-01 | Music Implementation Or Fixing the game | TRAINING SYSTEM in the companion app | Get & Post to database | Nuno
2021-01-01 | SFX implementation Or Fixing the game | TRAINING SYSTEM in the companion app | Get & Post to database | Gabriel
2021-01-08 | Interface - Pause Menu | *Undefined* | *Undefined* | Nuno
2021-01-08 | Interface - Main Game | *Undefined* | *Undefined* | Gabriel
2021-01-15 | Interface - Map | Optimizing/Solve of Problems if exist | Solve of Problems if exist | Nuno
2021-01-15 | Interface - Configuration Menu | Optimizing/Solve of Problems if exist | Solve of Problems if exist | Gabriel
2020-01-22 | Art Implementation | Optimizing/Solve of Problems if exist | Solve of Problems if exist | Nuno
2020-01-22 | Add Possible dubbers for the game | Optimizing/Solve of Problems if exist | Solve of Problems if exist | Gabriel
2020-01-29 | Fix Bugs and finish Game until 03/02 | Optimizing/Solve of Problems if exist | Solve of Problems if exist | Nuno
2020-01-29 | Fix Bugs and finish Game until 03/02 | Optimizing/Solve of Problems if exist | Solve of Problems if exist | Gabriel
2021-02-05 | -- | -- | -- | --
2021-02-05 | -- | -- | -- | --